## Chrome
Desktop | [6 empty] | Mobile (iPhone 7 using Chrome app
Area | Step | Input | Output | Status | Notes | Maps to test case/step | Status | Notes
Search Page | 1 | Access search from Homepage | The revised version of the Search screen is loaded | Complete | Dave's Comments |  | Complete
| 2 |  | The load time is adequate | Complete | Live is taking 25-30 seconds today (18/07/19) | Test step 1 Startup Process (\\Katalon Studio\Start\Test Cases\Reusable_Test_Sequences) | Complete
| 3 |  | Works on Google Chrome browser | Complete | YES | Test step 1 Startup Process (Startup sequence, Browser Selection) | Complete
| 4 | Trade Category Input box | Select categories | Complete | All searches Use multiple datasets to verify functionality parameterised, data driven | Test step 2 | In Progress | • Categories with long name do not show subheadings
| 5 | Location Input box | Search county | Complete | ? My example doesn't work (Fireplaces/stoves in Kent | Test step 3 | Complete | Location not found
| 6 | Location Input box | Search town/city | Complete | parameterised, data driven | Test step 3 | Complete
| 7 | Location Input box | Search postcode | Complete | parameterised, data driven | Test step 3 | Complete
| 8 | Improve your search pop-up | Cookie created, pop-up appears on search page load | Complete | From Homepage and repeat searches from the Search Page | Test step 1 Startup Process (Cookie nag detected and closed) | In Progress | • Only appears once when you first make a search - Rich looking into as working different on desktop and mobile
| 9 | Improve your search pop-up | Dismiss search pop-up | Complete | Pop-up must not re-appear once the cookie is set | Test step 1 Startup Process (Cookie nag detected and closed) | Complete
| 10 | Improve your search pop-up | Search by postcode, pop-up doesn't appear | Complete | Yes |  | Complete
| 11 | Page Title | Category' in 'location' | Complete | Yes |  | Complete
| 12 | Breadcrumb | Checkatrade>Search 'trade' in 'location' | Complete | WIP |  | Complete
| 13 | Breadcrumb | Checkatrade' links to Homepage | Complete | WIP • Breadcrumb "Checkatrade > Search 'trade' in 'location' takes you to LIVE not Current DEV (Jon W looking at) • Chris confirmed as expected, it’s the way the breadcrumb works | Need to verify the returned page relates to the current test environment DH | Complete
| 14 | Map | Map On | In Progress | WIP • Map jumps when "clicking on" and refreshing search (Rich has a fix to reduce the jumpiness) |  | In Progress | • Map key - Customer review drops off onto another line without the key icon
| 15 | Map | Map Off | Complete | WIP• Off by default |  | Complete
| 16 | Sort By: | Nearest Me | Complete | WIP • Sort by drop down - lot of space, looks off centre • If Selecting a "sort by" when the map is on the map jumps |  | Complete
| 17 | Sort By: | Most Relevant | Complete | WIP |  | Complete
| 18 | Sort By: | Most Feedback | Complete | WIP |  | Complete
| 19 | Sort By: | Closest feedback to me | Complete | WIP |  | In Progress | • "Closet Feedback", "Most recent feedback", "Longest serving member" cuts off when choosing from drop down (doesn't happen on live)
| 20 | Sort By: | Most recent feedback | Complete | WIP |  | In Progress
| 21 | Sort By: | Longest serving member | Complete | WIP |  | In Progress
| 22 | Pagination | Top Pagination | Complete | WIP |  | In Progress | • "Next" floats in the middle and looks off
| 23 | Pagination | Bottom Pagination | Complete | WIP |  | In Progress
| 24 | Select Trader | Whole panel clickable | Complete | WIP |  | Complete
| 25 | Member profile breadcrumb | Back to results | Complete | WIP |  | Complete
| 26 | Member profile breadcrumb | Next' to move forward to next profile. Navigates current page only | Complete | • Some accounts error when naivgating through - Chris confirmed all due to solr |  | Complete
| 27 | Member profile breadcrumb | Previous' to move back to the previous profile. Navigates current page only | Complete | WIP |  | Complete
| 28 | Directory panel | In position 4 in the search results (all pages) | Complete | WIP |  | Complete
| 29 | Directory Panel | Trader profile has back to search breadcrumb only | In Progress | WIP • Next & previous are displayed and active. Not going in directory panel order either |  | In Progress | • Next & previous are displayed and active. Not going in directory panel order either
| 30 | CAT Now banner | Links to Cat Now product page /Now?cat=0 | Complete | WIP • In trial location only |  | Complete
| 31 | Trader listing detail | Based in… | Complete | WIP • Detail present |  | Complete | • Detail present • The longer the area the distance goes onto a new line
| 32 | Trader listing detail | Member since…. | Complete | WIP • Detail present |  | Complete | • Detail present
| 33 | Trader listing detail | Average score | Complete | WIP • Detail present • Average score is incorrect - Chris confirmed due to solr |  | Complete | • Detail present
| 34 | Trader listing detail | Review count | Complete | • Detail present • Feedback count is incorrect - Chris confirmed due to solr |  | Complete | • Detail present
| 35 | Trader listing detail | Trader Search Appearance text | Complete | • Detail present |  | Complete | • Detail present
| 36 | SEO landing pages | Recently viewed' panel | Complete |  |  | Complete | Displays within the filter
| 37 | SEO landing pages | Alternative searches' panel | Complete | • Areas don't match - is this expected behaviour? |  | Complete | • Areas don't match - is this expected behaviour?
| 38 | Filters | Category - interaction updates breadcrumb | Complete | WIP |  | Complete
| 39 | Filters | Mobile version - open | Not Started | WIP N/A |  | Not Started
| 40 | Filters | Mobile version - clear filter | Not Started | WIP N/A |  | Not Started
| 41 | Filters | Mobile Version - close on 'X' | Not Started | WIP N/A |  | Not Started
| 42 | Filters | Mobile Version - Count of applied filter critieria | Not Started | WIP N/A |  | Not Started
| 43 | Filters | Category - expand/minimise | In Progress | WIP • Diamond Drilling is missing from builder category - Jon W thinks due to data • Expanding the category and selecting one further down the list doesn't display at the top fitler - fixing at a later date |  | In Progress | • Diamond Drilling is missing from builder category - Jon W thinks due to data • Expanding the category and selecting one further down the list doesn't display at the top fitler - fixing at a later date
| 44 | Filters | Distance | Complete | WIP • When lowering the distance to 10 miles, more results available appear. When clicking show this member, the also skilled in this trade isn't highlighted |  | Complete | • When lowering the distance to 10 miles, more results available appear. When clicking show this member, the also skilled in this trade isn't highlighted • You cannot remove/clear the filter "Clicking also skilled members in this trade" as it doesn't appear on mobile or filters
| 45 | Filters | Local Feedback | Complete | WIP • Reviews do not match - Chris confirmed due to solr |  | Complete | • Reviews do not match - Chris confirmed due to solr
| 46 | Filters | Search Feedback | Complete | WIP • Keywords not made bold - Chris confirmed due to solr issue/design • "Feedback containing xxx" appears twice underneath the field box and also at the top - Chris confirmed this is by design |  | Complete | • Keywords not made bold - Chris confirmed due to solr issue/design • "Feedback containing xxx" appears twice underneath the field box and also at the top - Chris confirmed this is by design
| 47 | Filters | Recent Feedback | Complete | WIP |  | Complete
| 48 | Filters | Work Type | In Progress | WIP • Removed commerical from member account. Due to solr, Chris confirmed may only be able to validate on live • Work type doesn't allow you to select both like live - Chris confirmed this is ok • Filters do not apply for web category "stone mason" |  | Complete
| 49 | Filters | Advanced Filters | Complete | WIP |  | Complete
| 50 | Filters | Accreditations | Complete | WIP |  | Complete
| 51 | Filters | Accreditations - expand / collapse | Complete | WIP |  | Complete
| 52 | Filters | Local Feedback - remove | Complete | WIP |  | Complete
| 53 | Filters | Search Feedback - remove | Complete | WIP |  | In Progress | • Clicking "Clear" does not clear the filter
| 54 | Filters | Recent Feedback - remove | Complete | WIP |  | Complete
| 55 | Filters | Work Type - remove | Complete | WIP |  | Complete
| 56 | Filters | Advanced Filters - remove | Complete | WIP |  | Complete
| 57 | Filters | Accreditations - remove | Complete | WIP |  | Complete
| 58 | More Info CTA | CTA links to the Trader profile | Not Started | • 404 error when clicking "more info" for member The Heating Company (GB) Ltd • Clicking contact info will then remove the "call button" Secure mobiles are displaying but cannot reference across admin |  | Not Started
| 59 | Contact Info CTA | CTA links to the Trader profile - non-Secure Contact Members only | Not Started | WIP |  | Not Started
| 60 | Call CTA | CTA to expose Secure Contact phone numbers | Not Started | WIP |  | Not Started
| 61 | Shortlist CTA | NOT visible, out of scope | Not Started | WIP |  | Not Started
| 62 | Scrolling | Filter and sort held on-screen in mobile view | Not Started | N/A |  | Not Started
| 63 | Error Pages | Error fetching your location | Not Started | WIP |  | Complete
| 64 | Error Pages | You have not completed a search | Complete | WIP |  | Not Started | • Couldn’t replicate
| 65 | Error Pages | (No results) Please try broadening your search | Complete | WIP |  | Not Started | • Couldn’t replicate
| 66 | Error Pages | (General error) Search Not Available | Complete | WIP |  | Not Started | • Couldn’t replicate
| 67 | Error Pages | No category or postcode selected | Complete | WIP |  | Complete
| 68 | Error Pages | No category selected | Complete | WIP |  | Complete
| 69 | Error Pages | (Serch exception) Please try your search again | Complete | WIP |  | Not Started | • Couldn’t replicate
| 70 | Error Pages | Unable to find the location | Complete | WIP |  | Complete
| 71 | Error Pages | (Ambiguous location e.g Sutton) Did you mean? | Complete | WIP |  | Complete
| 72 | Footer |  | Not Started | WIP |  | Not Started

## Microsoft Edge
Desktop | [5 empty] | Mobile
Area | Step | Input | Output | Status | Notes | Status | Notes
Search Page | 1 | Access search from Homepage | The revised version of the Search screen is loaded | Complete | Dave's Comments | Not Started | Chris Byrom tested edge on mobile
| 2 |  | The load time is adequate | Complete | Live is taking 25-30 seconds today (18/07/19) | Not Started
| 3 |  | Works on Microsoft Edge browser | Complete | YES | Not Started
| 4 | Trade Category Input box | Select categories | Complete | YES | Not Started
| 5 | Location Input box | Search county | Complete | ? My example doesn't work (Fireplaces/stoves in Kent | Not Started | Location not found
| 6 | Location Input box | Search town/city | Complete | YES | Not Started
| 7 | Location Input box | Search postcode | Complete | YES | Not Started
| 8 | Improve your search pop-up | Cookie created, pop-up appears on search page load | Complete | From Homepage and repeat searches from the Search Page | Not Started
| 9 | Improve your search pop-up | Dismiss search pop-up | Complete | Pop-up must not re-appear once the cookie is set | Not Started
| 10 | Improve your search pop-up | Search by postcode, pop-up doesn't appear | Complete | Yes | Not Started
| 11 | Page Title | Category' in 'location' | Complete | Yes | Not Started
| 12 | Breadcrumb | Checkatrade>Search 'trade' in 'location' | Complete |  | Not Started
| 13 | Breadcrumb | Checkatrade' links to Homepage | Complete | • Breadcrumb "Checkatrade > Search 'trade' in 'location' takes you to LIVE not Current DEV (Jon W looking at) Chris confirmed as expected, it’s the way the breadcrumb works | Not Started
| 14 | Map | Map On | Complete | • Map jumps when "clicking on" and refreshing search (Rich has a fix to reduce the jumpiness) | Not Started
| 15 | Map | Map Off | Complete | • Off by default | Not Started
| 16 | Sort By: | Nearest Me | Complete | • Sort by drop down - lot of space, looks off centre If Selecting a "sort by" when the map is on the map jumps | Not Started
| 17 | Sort By: | Most Relevant | Complete | • Drop down selection collapses different to chrome Chris confirmed this is due to different browsers | Not Started
| 18 | Sort By: | Most Feedback | Complete |  | Not Started
| 19 | Sort By: | Closest feedback to me | Complete |  | Not Started
| 20 | Sort By: | Most recent feedback | Complete |  | Not Started
| 21 | Sort By: | Longest serving member | Complete |  | Not Started
| 22 | Pagination | Top Pagination | Complete |  | Not Started
| 23 | Pagination | Bottom Pagination | Complete |  | Not Started
| 24 | Select Trader | Whole panel clickable | Complete | •Line underneath company name is continuous and goes through brackets and letters •Companies that have long names are not on one line - Chris confirmed they can wrap onto multiple lines | Not Started
| 25 | Member profile breadcrumb | Back to results | Complete |  | Not Started
| 26 | Member profile breadcrumb | Next' to move forward to next profile. Navigates current page only | Complete |  | Not Started
| 27 | Member profile breadcrumb | Previous' to move back to the previous profile. Navigates current page only | Complete |  | Not Started
| 28 | Directory panel | In position 4 in the search results (all pages) | Complete |  | Not Started
| 29 | Directory Panel | Trader profile has back to search breadcrumb only | Complete |  | Not Started
| 30 | CAT Now banner | Links to Cat Now product page /Now?cat=0 | Complete | • In trial location only | Not Started
| 31 | Trader listing detail | Based in… | Complete | • Detail present | Not Started | • Detail present
| 32 | Trader listing detail | Member since…. | Complete | • Detail present | Not Started | • Detail present
| 33 | Trader listing detail | Average score | Complete | • Detail present | Not Started | • Detail present
| 34 | Trader listing detail | Review count | Complete | • Detail present | Not Started | • Detail present
| 35 | Trader listing detail | Trader Search Appearance text | Complete | • Detail present | Not Started | • Detail present
| 36 | SEO landing pages | Recently viewed' panel | Complete |  | Not Started
| 37 | SEO landing pages | Alternative searches' panel | Complete |  | Not Started
| 38 | Filters | Category - interaction updates breadcrumb | Complete |  | Not Started
| 39 | Filters | Mobile version - open | Not Started | N/A | Not Started
| 40 | Filters | Mobile version - clear filter | Not Started | N/A | Not Started
| 41 | Filters | Mobile Version - close on 'X' | Not Started | N/A | Not Started
| 42 | Filters | Mobile Version - Count of applied filter critieria | Not Started | N/A | Not Started
| 43 | Filters | Category - expand/minimise | In Progress | • Expanding the category and selecting one further down the list doesn't display at the top fitler - fixing at a later date | Not Started
| 44 | Filters | Distance | Complete | • When lowering the distance to 10 miles, more results available appear. When clicking show this member, the also skilled in this trade isn't highlighted | Not Started
| 45 | Filters | Local Feedback | Complete |  | Not Started
| 46 | Filters | Search Feedback | Complete | • Keywords not made bold - Chris confirmed due to solr issue/design • "Feedback containing xxx" appears twice underneath the field box and also at the top - Chris confirmed this is by design | Not Started
| 47 | Filters | Recent Feedback | Complete |  | Not Started
| 48 | Filters | Work Type | Complete | • Doesn't allow you to select both domestic and commercial - Chris confirmed this is ok | Not Started
| 49 | Filters | Advanced Filters | Complete |  | Not Started
| 50 | Filters | Accreditations | Complete |  | Not Started
| 51 | Filters | Accreditations - expand / collapse | Complete |  | Not Started
| 52 | Filters | Local Feedback - remove | Complete |  | Not Started
| 53 | Filters | Search Feedback - remove | Complete |  | Not Started
| 54 | Filters | Recent Feedback - remove | Complete |  | Not Started
| 55 | Filters | Work Type - remove | Complete |  | Not Started
| 56 | Filters | Advanced Filters - remove | Complete |  | Not Started
| 57 | Filters | Accreditations - remove | Complete |  | Not Started
| 58 | More Info CTA | CTA links to the Trader profile | Not Started | • More info button swirls around | Not Started
| 59 | Contact Info CTA | CTA links to the Trader profile - non-Secure Contact Members only | Not Started |  | Not Started
| 60 | Call CTA | CTA to expose Secure Contact phone numbers | Not Started |  | Not Started
| 61 | Shortlist CTA | NOT visible, out of scope | Not Started |  | Not Started
| 62 | Scrolling | Filter and sort held on-screen in mobile view | Not Started | N/A | Not Started
| 63 | Error Pages | Error fetching your location | Not Started | WIP | Not Started
| 64 | Error Pages | You have not completed a search | Complete | WIP | Not Started
| 65 | Error Pages | (No results) Please try broadening your search | Complete | WIP | Not Started
| 66 | Error Pages | (General error) Search Not Available | Complete | WIP | Not Started
| 67 | Error Pages | No category or postcode selected | Complete | WIP | Not Started
| 68 | Error Pages | No category selected | Complete | WIP | Not Started
| 69 | Error Pages | (Serch exception) Please try your search again | Not Started | WIP | Not Started
| 70 | Error Pages | Unable to find the location | Complete | WIP | Not Started
| 71 | Error Pages | (Ambiguous location e.g Sutton) Did you mean? | Complete | WIP | Not Started
| 72 | Footer |  | Not Started |  | Not Started

## Internet Explorer
Desktop | [5 empty] | Mobile
Area | Step | Input | Output | Status | Notes | Status | Notes
Search Page | 1 | Access search from Homepage | The revised version of the Search screen is loaded | Complete | Dave's Comments | Not Started
| 2 |  | The load time is adequate | Complete | Live is taking 25-30 seconds today (18/07/19) | Not Started
| 3 |  | Works on Internet Explorer | Complete | YES | Not Started
| 4 | Trade Category Input box | Select categories | Complete | YES | Not Started
| 5 | Location Input box | Search county | Complete | ? My example doesn't work (Fireplaces/stoves in Kent | Not Started | Location not found
| 6 | Location Input box | Search town/city | Complete | YES | Not Started
| 7 | Location Input box | Search postcode | Complete | YES | Not Started
| 8 | Improve your search pop-up | Cookie created, pop-up appears on search page load | Complete | From Homepage and repeat searches from the Search Page | Not Started
| 9 | Improve your search pop-up | Dismiss search pop-up | Complete | Pop-up must not re-appear once the cookie is set | Not Started
| 10 | Improve your search pop-up | Search by postcode, pop-up doesn't appear | Complete | Yes | Not Started
| 11 | Page Title | Category' in 'location' | Complete | Yes | Not Started
| 12 | Breadcrumb | Checkatrade>Search 'trade' in 'location' | In Progress | • Breadcrumb doesn't appear | Not Started
| 13 | Breadcrumb | Checkatrade' links to Homepage | Not Started | • Navigate back to the homepage | Not Started
| 14 | Map | Map On | Not Started |  | Not Started
| 15 | Map | Map Off | Not Started | • Off by default | Not Started
| 16 | Sort By: | Nearest Me | Not Started |  | Not Started
| 17 | Sort By: | Most Relevant | Not Started |  | Not Started
| 18 | Sort By: | Most Feedback | Not Started |  | Not Started
| 19 | Sort By: | Closest feedback to me | Not Started |  | Not Started
| 20 | Sort By: | Most recent feedback | Not Started |  | Not Started
| 21 | Sort By: | Longest serving member | Not Started |  | Not Started
| 22 | Pagination | Top Pagination | Not Started |  | Not Started
| 23 | Pagination | Bottom Pagination | Not Started |  | Not Started
| 24 | Select Trader | Whole panel clickable | Not Started |  | Not Started
| 25 | Member profile breadcrumb | Back to results | Not Started |  | Not Started
| 26 | Member profile breadcrumb | Next' to move forward to next profile. Navigates current page only | Not Started |  | Not Started
| 27 | Member profile breadcrumb | Previous' to move back to the previous profile. Navigates current page only | Not Started |  | Not Started
| 28 | Directory panel | In position 4 in the search results (all pages) | Not Started |  | Not Started
| 29 | Directory Panel | Trader profile has back to search breadcrumb only | Not Started |  | Not Started
| 30 | CAT Now banner | Links to Cat Now product page /Now?cat=0 | Not Started | In trial location only | Not Started
| 31 | Trader listing detail | Based in… | Not Started | Detail present | Not Started | Detail present
| 32 | Trader listing detail | Member since…. | Not Started | Detail present | Not Started | Detail present
| 33 | Trader listing detail | Average score | Not Started | Detail present | Not Started | Detail present
| 34 | Trader listing detail | Review count | Not Started | Detail present | Not Started | Detail present
| 35 | Trader listing detail | Trader Search Appearance text | Not Started | Detail present | Not Started | Detail present
| 36 | SEO landing pages | Recently viewed' panel | Not Started |  | Not Started
| 37 | SEO landing pages | Alternative searches' panel | Not Started |  | Not Started
| 38 | Filters | Category - interaction updates breadcrumb | Not Started |  | Not Started
| 39 | Filters | Mobile version - open | Not Started | N/A | Not Started
| 40 | Filters | Mobile version - clear filter | Not Started | N/A | Not Started
| 41 | Filters | Mobile Version - close on 'X' | Not Started | N/A | Not Started
| 42 | Filters | Mobile Version - Count of applied filter critieria | Not Started | N/A | Not Started
| 43 | Filters | Category - expand/minimise | Not Started |  | Not Started
| 44 | Filters | Distance | Not Started |  | Not Started
| 45 | Filters | Local Feedback | Not Started |  | Not Started
| 46 | Filters | Search Feedback | Not Started |  | Not Started
| 47 | Filters | Recent Feedback | Not Started |  | Not Started
| 48 | Filters | Work Type | Not Started |  | Not Started
| 49 | Filters | Advanced Filters | Not Started |  | Not Started
| 50 | Filters | Accreditations | Not Started |  | Not Started
| 51 | Filters | Accreditations - expand / collapse | Not Started |  | Not Started
| 52 | Filters | Local Feedback - remove | Not Started |  | Not Started
| 53 | Filters | Search Feedback - remove | Not Started |  | Not Started
| 54 | Filters | Recent Feedback - remove | Not Started |  | Not Started
| 55 | Filters | Work Type - remove | Not Started |  | Not Started
| 56 | Filters | Advanced Filters - remove | Not Started |  | Not Started
| 57 | Filters | Accreditations - remove | Not Started |  | Not Started
| 58 | More Info CTA | CTA links to the Trader profile | Not Started |  | Not Started
| 59 | Contact Info CTA | CTA links to the Trader profile - non-Secure Contact Members only | Not Started |  | Not Started
| 60 | Call CTA | CTA to expose Secure Contact phone numbers | Not Started |  | Not Started
| 61 | Shortlist CTA | NOT visible, out of scope | Not Started |  | Not Started
| 62 | Scrolling | Filter and sort held on-screen in mobile view | Not Started | N/A | Not Started
| 63 | Error Pages | Error fetching your location | Not Started | WIP | Not Started
| 64 | Error Pages | You have not completed a search | Not Started | WIP | Not Started
| 65 | Error Pages | (No results) Please try broadening your search | Not Started | WIP | Not Started
| 66 | Error Pages | (General error) Search Not Available | Not Started | WIP | Not Started
| 67 | Error Pages | No category or postcode selected | Not Started | WIP | Not Started
| 68 | Error Pages | No category selected | Not Started | WIP | Not Started
| 69 | Error Pages | (Serch exception) Please try your search again | Not Started | WIP | Not Started
| 70 | Error Pages | Unable to find the location | Not Started | WIP | Not Started
| 71 | Error Pages | (Ambiguous location e.g Sutton) Did you mean? | Not Started | WIP | Not Started
| 72 | Footer |  | Not Started |  | Not Started

## Apple Safari
iPad (Landscape/Portrait) | [5 empty] | Mobile
Area | Step | Input | Output | Status | Notes | Status | Notes
Search Page | 1 | Access search from Homepage | The revised version of the Search screen is loaded | Complete | • Landscape tested THE LAST RELEASE OF SAFARI WAS IN 2012? • Portrait tested | Complete
| 2 |  | The load time is adequate | Complete | • Landscape tested • Portrait tested | Complete
| 3 |  | Works on Apple Safari | Complete | • Landscape tested • Portrait tested | Complete
| 4 | Trade Category Input box | Select categories | In Progress | • Landscape tested • Portrait tested • Portrait view - categories with long name do not show subheadings | Complete
| 5 | Location Input box | Search county | Complete | • Landscape tested • Portrait tested | Complete
| 6 | Location Input box | Search town/city | Complete | • Landscape tested • Portrait tested | Complete
| 7 | Location Input box | Search postcode | Complete | • Landscape tested • Portrait tested | Complete
| 8 | Improve your search pop-up | Cookie created, pop-up appears on search page load | Not Started | • From Homepage and repeat searches from the Search Page • Landscape tested • Portrait tested | Complete
| 9 | Improve your search pop-up | Dismiss search pop-up | Not Started | • Pop-up must not re-appear once the cookie is set • Landscape tested • Portrait test | Complete
| 10 | Improve your search pop-up | Search by postcode, pop-up doesn't appear | Complete | • Landscape tested • Portrait tested | Complete
| 11 | Page Title | Category' in 'location' | Complete | • Landscape tested • Portrait tested | Complete
| 12 | Breadcrumb | Checkatrade>Search 'trade' in 'location' | Complete | • Landscape tested • Portrait tested | Complete
| 13 | Breadcrumb | Checkatrade' links to Homepage | Complete | • Breadcrumb "Checkatrade > Search 'trade' in 'location' takes you to LIVE not Current DEV (Jon W looking at) Chris confirmed as expected, it’s the way the breadcrumb work • Landscape tested • Portrait tested | Complete
| 14 | Map | Map On | In Progress | • Map jumps when "clicking on" and refreshing search (Rich has a fix to reduce the jumpiness) • Landscape tested • Portrait tested • Portrait view - "XX member can help appears under the map. Doesn't appear on landscape - Chris confirmed this is dictated by size of screen • Portrait view - Map on is jumpy and pushes everything up | Complete
| 15 | Map | Map Off | Complete | • Off by default • Landscape tested • Portrait tested | Complete
| 16 | Sort By: | Nearest Me | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 17 | Sort By: | Most Relevant | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 18 | Sort By: | Most Feedback | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 19 | Sort By: | Closest feedback to me | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 20 | Sort By: | Most recent feedback | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 21 | Sort By: | Longest serving member | Complete | • Landscape tested • Portrait tested • Portrait view - drop down appears in the middle of the screen | Complete
| 22 | Pagination | Top Pagination | Complete | • Landscape tested • Portrait tested | Complete
| 23 | Pagination | Bottom Pagination | Complete | • Landscape tested • Portrait tested | Complete
| 24 | Select Trader | Whole panel clickable | Complete | • Landscape tested • Landscape View - Avg score and reviews are too close to members who have long names | Complete
| 25 | Member profile breadcrumb | Back to results | Complete | • Landscape tested • Portrait tested • Portrait view - back to results is too close to the business card | Complete
| 26 | Member profile breadcrumb | Next' to move forward to next profile. Navigates current page only | Complete | • Landscape tested • Portrait tested | Complete
| 27 | Member profile breadcrumb | Previous' to move back to the previous profile. Navigates current page only | Complete | • Landscape tested • Portrait tested • Portrait view - "Request callback is overlapping "checks and accreditations" not happening on live | Complete
| 28 | Directory panel | In position 4 in the search results (all pages) | Complete | • Landscape tested • Portrait tested | Complete
| 29 | Directory Panel | Trader profile has back to search breadcrumb only | In Progress | • Landscape tested • Portrait tested • Portrait & landscape view - Next & previous are displayed and active. Not going in directory panel order either | Complete
| 30 | CAT Now banner | Links to Cat Now product page /Now?cat=0 | Complete | • In trial location only • Landscape tested • Portrait tested | Complete
| 31 | Trader listing detail | Based in… | Complete | • Detail present • Landscape tested • Portrait tested | Complete | Detail present
| 32 | Trader listing detail | Member since…. | Complete | • Detail present • Landscape tested • Portrait tested | Complete | Detail present
| 33 | Trader listing detail | Average score | Complete | • Detail present • Landscape tested • Portrait tested | Complete | Detail present
| 34 | Trader listing detail | Review count | Complete | • Detail present • Landscape tested • Portrait tested | Complete | Detail present
| 35 | Trader listing detail | Trader Search Appearance text | Complete | • Detail present • Landscape tested • Portrait tested | Complete | Detail present
| 36 | SEO landing pages | Recently viewed' panel | Complete | • Detail present • Landscape tested • Portrait tested - Displays within filter | Complete
| 37 | SEO landing pages | Alternative searches' panel | Complete | • Detail present • Landscape tested • Portrait tested - Displays within filter | Complete
| 38 | Filters | Category - interaction updates breadcrumb | Complete | • Detail present • Landscape tested • Portrait tested | Complete
| 39 | Filters | Mobile version - open | Not Started | N/A | Complete
| 40 | Filters | Mobile version - clear filter | Not Started | N/A | Complete
| 41 | Filters | Mobile Version - close on 'X' | Not Started | N/A | Complete
| 42 | Filters | Mobile Version - Count of applied filter critieria | Not Started | N/A | Complete
| 43 | Filters | Category - expand/minimise | Complete | • Landscape tested • Expanding the category and selecting one further down the list doesn't display at the top fitler - fixing at a later date • Portrait tested - displays in filter section | Complete |  | Portrait view - You can only select one filter at a time and re-open it. Discussed with Chris
| 44 | Filters | Distance | Complete | • Landscape tested • Portrait tested | Complete
| 45 | Filters | Local Feedback | Complete | • Landscape tested • Portrait tested | Complete
| 46 | Filters | Search Feedback | Complete | • Landscape tested • Keywords not made bold - Chris confirmed due to solr issue/design "Feedback containing xxx" appears twice underneath the field box and also at the top - Chris confirmed this is by design • Portrait tested | Complete
| 47 | Filters | Recent Feedback | Complete | • Landscape tested • Portrait tested | Complete
| 48 | Filters | Work Type | Complete | • Landscape tested • Portrait tested | Complete
| 49 | Filters | Advanced Filters | Complete | • Landscape tested • Portrait tested | Complete
| 50 | Filters | Accreditations | Complete | • Landscape tested • Portrait tested | Complete
| 51 | Filters | Accreditations - expand / collapse | Complete | • Landscape tested • Portrait tested | Complete
| 52 | Filters | Local Feedback - remove | Complete | • Landscape tested • Portrait tested | Complete
| 53 | Filters | Search Feedback - remove | In Progress | • Landscape tested • Portrait tested • Clicking "clear" does not clear | Complete
| 54 | Filters | Recent Feedback - remove | Complete | • Landscape tested • Portrait tested | Complete
| 55 | Filters | Work Type - remove | Complete | • Landscape tested • Portrait tested | Complete
| 56 | Filters | Advanced Filters - remove | Complete | • Landscape tested • Portrait tested | Complete
| 57 | Filters | Accreditations - remove | Complete | • Landscape tested • Portrait tested | Complete
| 58 | More Info CTA | CTA links to the Trader profile | Not Started |  | Complete
| 59 | Contact Info CTA | CTA links to the Trader profile - non-Secure Contact Members only | Not Started |  | Complete
| 60 | Call CTA | CTA to expose Secure Contact phone numbers | Not Started |  | Complete
| 61 | Shortlist CTA | NOT visible, out of scope | Not Started |  | Complete
| 62 | Scrolling | Filter and sort held on-screen in mobile view | Not Started | N/A | Complete
| 63 | Error Pages | Error fetching your location | Not Started | • Couldn’t replicate | Complete
| 64 | Error Pages | You have not completed a search | Not Started | • Couldn’t replicate | Complete
| 65 | Error Pages | (No results) Please try broadening your search | Complete | • Landscape tested | In Progress
| 66 | Error Pages | (General error) Search Not Available | Complete | • Portrait tested | Not Started
| 67 | Error Pages | No category or postcode selected | Complete | • Landscape tested | Complete
| 68 | Error Pages | No category selected | Complete | • Landscape tested | Complete
| 69 | Error Pages | (Serch exception) Please try your search again | Not Started | • Couldn’t replicate | Not Started
| 70 | Error Pages | Unable to find the location | Complete | • Landscape tested • Portrait tested | Complete
| 71 | Error Pages | (Ambiguous location e.g Sutton) Did you mean? | Complete | • Landscape tested | Complete
| 72 | Footer |  | Not Started |  | Not Started

## FireFox
Desktop | [5 empty] | Mobile
Area | Step | Input | Output | Status | Notes | Status | Notes
Search Page | 1 | Access search from Homepage | The revised version of the Search screen is loaded | Complete | Dave's Comments | Not Started
| 2 |  | The load time is adequate | Complete | Live is taking 25-30 seconds today (18/07/19) | Not Started | After talking to Alex at 3pm, suddenly improved drastically
| 3 |  | Works on Firefox browser | Complete | YES | Not Started
| 4 | Trade Category Input box | Select categories | Complete | YES | Not Started
| 5 | Location Input box | Search county | Complete | ? My example doesn't work (Fireplaces/stoves in Kent | Not Started | Location not found
| 6 | Location Input box | Search town/city | Complete | YES | Not Started
| 7 | Location Input box | Search postcode | Complete | YES | Not Started
| 8 | Improve your search pop-up | Cookie created, pop-up appears on search page load | Complete | From Homepage and repeat searches from the Search Page | Not Started
| 9 | Improve your search pop-up | Dismiss search pop-up | Complete | Pop-up must not re-appear once the cookie is set | Not Started
| 10 | Improve your search pop-up | Search by postcode, pop-up doesn't appear | Complete | Yes | Not Started
| 11 | Page Title | Category' in 'location' | Complete | Yes | Not Started
| 12 | Breadcrumb | Checkatrade>Search 'trade' in 'location' | Not Started |  | Not Started
| 13 | Breadcrumb | Checkatrade' links to Homepage | Not Started | Navigate back to the homepage | Not Started
| 14 | Map | Map On | Not Started |  | Not Started
| 15 | Map | Map Off | Not Started | Off by default | Not Started
| 16 | Sort By: | Nearest Me | Not Started |  | Not Started
| 17 | Sort By: | Most Relevant | Not Started |  | Not Started
| 18 | Sort By: | Most Feedback | Not Started |  | Not Started
| 19 | Sort By: | Closest feedback to me | Not Started |  | Not Started
| 20 | Sort By: | Most recent feedback | Not Started |  | Not Started
| 21 | Sort By: | Longest serving member | Not Started |  | Not Started
| 22 | Pagination | Top Pagination | Not Started |  | Not Started
| 23 | Pagination | Bottom Pagination | Not Started |  | Not Started
| 24 | Select Trader | Whole panel clickable | Not Started |  | Not Started
| 25 | Member profile breadcrumb | Back to results | Not Started |  | Not Started
| 26 | Member profile breadcrumb | Next' to move forward to next profile. Navigates current page only | Not Started |  | Not Started
| 27 | Member profile breadcrumb | Previous' to move back to the previous profile. Navigates current page only | Not Started |  | Not Started
| 28 | Directory panel | In position 4 in the search results (all pages) | Not Started |  | Not Started
| 29 | Directory Panel | Trader profile has back to search breadcrumb only | Not Started |  | Not Started
| 30 | CAT Now banner | Links to Cat Now product page /Now?cat=0 | Not Started | In trial location only | Not Started
| 31 | Trader listing detail | Based in… | Not Started | Detail present | Not Started | Detail present
| 32 | Trader listing detail | Member since…. | Not Started | Detail present | Not Started | Detail present
| 33 | Trader listing detail | Average score | Not Started | Detail present | Not Started | Detail present
| 34 | Trader listing detail | Review count | Not Started | Detail present | Not Started | Detail present
| 35 | Trader listing detail | Trader Search Appearance text | Not Started | Detail present | Not Started | Detail present
| 36 | SEO landing pages | Recently viewed' panel | Not Started |  | Not Started
| 37 | SEO landing pages | Alternative searches' panel | Not Started |  | Not Started
| 38 | Filters | Category - interaction updates breadcrumb | Not Started |  | Not Started
| 39 | Filters | Mobile version - open | Not Started | N/A | Not Started
| 40 | Filters | Mobile version - clear filter | Not Started | N/A | Not Started
| 41 | Filters | Mobile Version - close on 'X' | Not Started | N/A | Not Started
| 42 | Filters | Mobile Version - Count of applied filter critieria | Not Started | N/A | Not Started
| 43 | Filters | Category - expand/minimise | Not Started |  | Not Started
| 44 | Filters | Distance | Not Started |  | Not Started
| 45 | Filters | Local Feedback | Not Started |  | Not Started
| 46 | Filters | Search Feedback | Not Started |  | Not Started
| 47 | Filters | Recent Feedback | Not Started |  | Not Started
| 48 | Filters | Work Type | Not Started |  | Not Started
| 49 | Filters | Advanced Filters | Not Started |  | Not Started
| 50 | Filters | Accreditations | Not Started |  | Not Started
| 51 | Filters | Accreditations - expand / collapse | Not Started |  | Not Started
| 52 | Filters | Local Feedback - remove | Not Started |  | Not Started
| 53 | Filters | Search Feedback - remove | Not Started |  | Not Started
| 54 | Filters | Recent Feedback - remove | Not Started |  | Not Started
| 55 | Filters | Work Type - remove | Not Started |  | Not Started
| 56 | Filters | Advanced Filters - remove | Not Started |  | Not Started
| 57 | Filters | Accreditations - remove | Not Started |  | Not Started
| 58 | More Info CTA | CTA links to the Trader profile | Not Started |  | Not Started
| 59 | Contact Info CTA | CTA links to the Trader profile - non-Secure Contact Members only | Not Started |  | Not Started
| 60 | Call CTA | CTA to expose Secure Contact phone numbers | Not Started |  | Not Started
| 61 | Shortlist CTA | NOT visible, out of scope | Not Started |  | Not Started
| 62 | Scrolling | Filter and sort held on-screen in mobile view | Not Started | N/A | Not Started
| 63 | Error Pages | Error fetching your location | Not Started | WIP | Not Started
| 64 | Error Pages | You have not completed a search | Not Started | WIP | Not Started
| 65 | Error Pages | (No results) Please try broadening your search | Not Started | WIP | Not Started
| 66 | Error Pages | (General error) Search Not Available | Not Started | WIP | Not Started
| 67 | Error Pages | No category or postcode selected | Not Started | WIP | Not Started
| 68 | Error Pages | No category selected | Not Started | WIP | Not Started
| 69 | Error Pages | (Serch exception) Please try your search again | Not Started | WIP | Not Started
| 70 | Error Pages | Unable to find the location | Not Started | WIP | Not Started
| 71 | Error Pages | (Ambiguous location e.g Sutton) Did you mean? | Not Started | WIP | Not Started
| 72 | Footer |  | Not Started |  | Not Started