## Sheet1
Regression Test | Reference Document/Script Location | Description | Comment | Environment | Test Execution Timing
Test Cases/Scenarios/E2E
a_Header_Template | Template for new test cases/suites |  |  |  | End 08-01-2019 10:24:54 AM
Default Device |  |  | Will convert this test to run on Mobile Device Emulations
Sunny Day Scenarios | 5 different screen resolutions now tested | Multi resolution - | 400x600, 500x700, 600x800, 700x900 and 800x1000 |  | Start 08/01/2019 10:00:51 AM
|  | search and verifies outcome |  |  | End 08-01-2019 10:01:10 AM
Give_Feedback | 5 Primary - E2E paths covered | 10 Test Steps (data entry for each page counted as 1 test step) | E2E Process in place, Fills each form and progresses to the next page (data on spreadsheet so extendable), verifies completion and return to home on completion |  | 42 Seconds (1 iteration of data)
Give_Feedback - Negative |  | 90% Complete - | On Hold, Low Priority
Give_Feedback - Validation |  | 10 Test Steps (data entry for each page counted as 1 test step) | Checks Verification Messages for each page of the process, completes E2E and Commits |  | 30 Seconds
Members_Area
Members Area Integrity Checks | WIP - Regression Spreadsheet V2 |  | Review | Current Task
Advertise Directory |  |  | Added to Master test Suite
Callback Requests |  |  | Added to Master test Suite
Community |  |  | Added to Master test Suite
Members AcceptaCard |  |  | Added to Master test Suite
Members Achievements |  |  | Added to Master test Suite
Members Contact Preferences
Members Featured Items
Members Marketing Materials
Members Policy Terms and Conditions |  |  | Added to Master test Suite
Members Scams
Members Team Photos
Members Trading Standards
Members Whistle Blower |  |  | Added to Master test Suite
My Feedback |  |  | Added to Master test Suite
My Membership |  |  | Added to Master test Suite
My Photos |  |  | Added to Master test Suite
My Profile Page |  |  | Added to Master test Suite
My Stats |  |  | Added to Master test Suite
Offers Discounts
Payments |  |  | Added to Master test Suite
Payments validation
Received NegativeReview |  |  | Added to Master test Suite
Useful_Documents |  |  | Added to Master test Suite
Trades Apply Here | Regression Spreadsheet V2 | Trades Apply Here function, Joining/Membership Application. |  | Preview
Sunny Day Scenarios |  | 11 test steps + startup and teardown sequences | Test currently verifies the CONGRATULATIONS screen is returned on completion |  | Start 08/01/2019 09:55:25 AM
|  |  | Currently no Web Office back end check - future enhancement |  | End 08-01-2019 09:55:56 AM
Trades Apply Here Validation |  |  | Refactored test, all test steps moved to reuse folder, aiding resilience and maintainability |  | 31 Seconds
Sunny Day Scenarios |  | 23 test steps + startup and teardown sequences | Validation Checks |  | 23 Seconds
Trade Location Search | Search Page Test Plan | Search on Trade and Location | Uses a datapool (Excel spreadsheet) to iterating through 10 variations of test data | Live/Preview | Start 08/01/2019 10:06:16 AM
Sunny Day Scenario | 5-10 E2E - paths covered |  | working on Preview (about 25% of Search Page Test Plan Covered) |  | End 08/01/2019 10:07:22 AM
|  | 9 test steps + startup and teardown sequences | Refactored, for later easier maintenance |  | 66 Seconds
Trade Location Search Error Messages/Validation |  | TODO
Sequential execution - Trade Location Search
Trade Name/Number Search |  | Search on Trade Name or Checkatrade ID | Uses a datapool (Excel spreadsheet) to iterating through 10 variations of test data |  | Start 08-01-2019 10:12:32 AM
Sunny Day Scenario | 5-10 - E2E paths covered |  | working on Preview (about 25% of Search Page Test Plan Covered) |  | End 08-01-2019 10:14:00 AM
Web Office Header Search |  |  | Added to Master test Suite
Web Office Companies Top |  |  | Added to Master test Suite
Web Office Directories Top |  |  | Added to Master test Suite
Web Office Feedback Top |  |  | Added to Master test Suite
Web Office Consumers Top |  |  | Added to Master test Suite
Web Office Cases Top |  |  | Added to Master test Suite
Web Office Reports Top |  |  | Added to Master test Suite |  | 88 Seconds
Start 08-01-2019 10:23:55 AM
Test Suites |  |  | Refactored, for later easier maintenance |  | 59 Seconds
10 minutes per browser (execution timing)
Test Suite Collection 200819 (Master) |  | Currently runs on Chrome and Firefox | Runs ALL Available (can be executed using 'CAT_Regression_Batch.bat') |  | 20 minutes test execution time
Give Feedback |  |  | 5 different scenarios from very positive to very negative
Give Feedback Validation |  |  | E2E and Validation Tests
Members Area Integrity Checks | Superceeded
Members Area - AcceptaCard
Members Area - Achievements
Members Area - Callback
Members Area - Advertising
Members Area - My Community
Members Area - My Feedback
Members Area - My Membership
Members Area - My payments
Members Area - My Photos
Members Area - My Profile
Members Area - My Stats |  |  | 5 different scenarios from very positive to very negative |  | Start 08-01-2019 10:23:55 AM
Members Area - Received Negative Feedback
Members Area - Terms and conditions
Members Area - Whistle Blower
Members Area - Useful Documents
Mobile Devices (screen resolution Test) |  |  | 5 Screen Sizes
Trades Apply Here |  |  | E2E and Validation Tests
Trades Apply Here Validation
Parallel Execution (8 concurrent instances)
Trade Location Search | Search Page Test Plan |  | As defined test case above, but run across 4 browsers (Chrome/IE/Ffox/Edge) |  | Start 08-01-2019 10:30:12 AM
Sunny Day Scenarios |  |  |  |  | End 08-01-2019 10:31:37 AM
85 Seconds
Trade Name/Number Search |  |  | As defined test case above, but run across 4 browsers (Chrome/IE/Ffox/Edge) |  | Sequential execution - Trade Name Search
Sunny Day Scenarios |  |  |  |  | Start 08-01-2019 10:40:36 AM
Web Office - Header Search
Web Office - Top Level - Cases Top
Web Office - Top Level - Companies Top
Web Office - Top Level - Consumers Top
Web Office - Top Level - Directories Top
Web Office - Top Level - Feedback Top
Web Office - Top Level - Reports Top
61 Seconds
Reusable Test Steps/Sequences | Project (Item) Location |  |  |  | Parallel Execution (8 concurrent instances)
Start 08-01-2019 10:46:08 AM
List below to be updated TODO (17/12/2019) | Reusable Test Sequences |  | Refactored test steps for reuse across the regression test project |  | End 08-01-2019 10:47:35 AM
87 Seconds
CAT_Click_Search_Trade_Name
CAT_Enter_Trade_Classification
CAT_Enter_Trade_Location
CAT_Enter_Trade_Name |  |  | Name or Checkatrade ID parsed in
CAT_Hit_Search_Button
CAT_Home
CAT_Scroll_to_Footer
CAT_Scroll_To_Search_Button
CAT_Search_Trade_Name
CAT_Setup
CAT_Teardown
CAT_Verification |  |  | Confirms concantinated text of trade+" In "+Location
CAT_Verification_Location |  |  | Confirms Location
CAT_Verification_Primary_Contact |  |  | Confirms Primary Contact name
URL_Handler |  |  | Handles current test environment URL Discrepencies
| Reusable Test Sequences/Banner_Menu |  | Navigation
Advice
Callback_List
Checkatrade_logo
Consumer_Zone
GiveFeedback
Trades_Apply_Here
Tradse_Sign_In
Reusable Test Sequences/Give_Feedback
Final_Page
Hit_Next
Which_Member_To_Review
Reusable Test Sequences/Give_Feedback/Further_Information
Further_Information
Further_Information_Validation
Reusable Test Sequences/Give_Feedback/Validation
Please_Select_An_Answer
Please_Supply_Home_telephone_Nimber
Score_Trader |  |  | Prompt to enter between 0 and 10
Reusable Test Sequences/Give_Feedback/Your_Details
Checkatrade_Questions
Consumer_or_Customer_Selection
Contact_Details_Formfill
Hit_Your_Details
Personal_Details_Formfill
Your_Details
Your_Details_Validation
Reusable Test Sequences/Give_Feedback/Your_Experience
Feedback_Knowledge
Not_Recommend
Quotation_Selection
Recommendation_Selection
Your_Experience
Your_Experience_Validation
Reusable Test Sequences/Give_Feedback/Your_Experience/Validation
Your_Experience_Initial_Page_State
Your_Experience_Page_State_Nothing_Set
Reusable Test Sequences/Give_Feedback/Your_Scores
Courtesy_Selection
Details_of_work_Done_Formfill
Details_of_work_Done_Formfill_ALT
Hit_Next
Quality_of_Workmanship_selection
Reliability_Timekeeping_Selection
Tidiness_Selection
Your_Scores
Your_Scores_ALT
Your_Scores_List_Box_Selection
Your_Scores_List_Box_Selection_ALT
Your_Scores_Validation
| Reusable Test Sequences/Members Area |  | Checked to here - 17/12/2019
Log_On
Start_Up
Navigate_Membership_Area
Reusable Test Sequences/Members Area/Area_Menu/Grow_Your_Business
Advertise
My_Photos
My_Profile
My_Stats
Reusable Test Sequences/Members Area/Area_Menu/Grow_Your_Business/Profiles
Banner_Image
Company_Logo
Insurance
Maximise_Your_Profile
Profile_Text
Search_Appearances
Vetting_Information
Where_You_Work
Reusable Test Sequences/Members Area/Area_Menu/Your_Account
Membership
Offers
Payments
Useful_Documents
Reusable Test Sequences/Members Area/Area_Menu/Your_Customers
Callback_Request
My_Feedback
Received_Negative_Review
Reusable Test Sequences/Members Area/Area_Menu/Your_Customers/Feedback
Awareness
Published_Feedback
Published_Feedback_Search
Remind_Customer
Remind_Customer_Sent
Your_Customers
Reusable Test Sequences/Members Area/Banner Menu
Contact_Us
Dashboard
Grow_Your_Business
Log_Off
Recommend_a_Friend
Your_Account
Your_Customers
Reusable Test Sequences/Members Area/Profile
Profile_Text_Update
Reusable Test Sequences/Members Area/Validation
Advertise
Awareness
Callback_Requests
Home_Page
Membership
My_Feedback
My_Photo
My_Profile
My_Stats
Offers
Payments
Receive_Negative_Review
Remind_Customers
Useful_Documents
Your_Customers
Reusable Test Sequences/Members Area/Validation/Profiles
Banner_Image
Company_Logo
Insurance
Maximise_Your_Profile
Profile_Text
Search_Appearances
Vetting_Informtion
Where_You_Work
Reusable Test Sequences/Members Area/Validation/Profiles/Vetting_Information_Sub
Add_Accreditation
Services_Section
Reusable Test Sequences/TRADES_Application
Congratulations_Reported
Hit-Signup
Hit_Submit
Lookup_Trade_Category
Postcode_Prompt
Set_Company_Name
Set_Contact_Number
Set_Email_Address
Set_Full_Name
Set_INVALID_Email_Address
Set_NULL_Data_in_Fields_Containing_Invalid_Data
Set_Postcode
Set_Random_Data_In_Empty_Fields
Set_Trade_Category
Reusable Test Sequences/TRADES_Application/Validation
Please_Enter_Valid_Email
Please_Specify_Valid_Phone_Number
Sorry_No_Results_Found
This_Field_Is_Required
Reusable Test Sequences/Sign_Up
Trades_Apply_Here
Trades_Apply_Here_Validation
Reusable Test Sequences/Verification_Checks
Reusable Test Sequences/Web_Office
Case_Opened
Web_Office |  |  | TODO
Web_Office_Smoke
END